## CNG STATION
Design of a CNG System at a Liquid Fuel Gas Station Prepared by:Junior Charles | Planned Start Date | Planned End Date | Planned Duration | Design of a CNG System at a Liquid Fuel Gas Station (Estimated 15 Weeks Duration)
|  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15
|  |  |  | Jan 6th- 12th | [6 empty] | Jan 13th- 19th | [6 empty] | Jan 20th- 26th | [6 empty] | Jan27th- Feb 2nd | [6 empty] | Feb 3rdth-9th | [6 empty] | Feb 10th-16th | [6 empty] | Feb 17th-23rd | [6 empty] | Feb24th- Mar 2nd | [6 empty] | Mar 3rd- 9th | [6 empty] | Mar 10th- 16th | [6 empty] | Mar 17th- 23rd | [6 empty] | Mar 24th- 30th | [6 empty] | Mar31st- Apr-6th | [6 empty] | Apr 7thth- 13th | [6 empty] | April 14- 20th
| Date | Date | Week | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon
Proposal | Date: Jan 6th; Date: Feb 16th; Week: 6 Weeks; Jan 6th- 12th Mon: Project Proposal (6 Weeks)
Restate Problem and Select Project Solution | Date: Jan 6th; Date: Jan 19th; Week: 2 Weeks; Jan 6th- 12th Mon: Restate Problem and Select Proj Solution (2 Weeks)
Perform Secondary Research | Date: Jan 20th; Date: Jan 26th; Week: 1 Week; Jan 20th- 26th Mon: Secondary Research (1 Week)
Create Project Plan | Date: Jan 27th; Date: Feb 9th; Week: 2 Weeks; Jan27th- Feb 2nd Mon: Design Project Plan (2 Weeks)
Perform Feasibility Study | Date: Feb 3rd; Date: Feb 16th; Week: 2 weeks; Feb 3rdth-9th Mon: Perform Feasibility Study (2 Weeks)
Determine Legislation Ethics on Decision Making | Date: Feb 3rd; Date: Feb 16th; Week: 2 Weeks; Feb 3rdth-9th Mon: Determine Legislation Ethics on Decision Making (2 Weeks)
Prepare Logbooks | Date: Jan 6th; Date: April 20th; Week: 15 Weeks; Jan 6th- 12th Mon: Prepare Logbooks (15 Weeks)
Project Report | Date: Feb 17th; Date: Apr 6th; Week: 7 Weeks; Feb 17th-23rd Mon: Project Report (7 Weeks)
Conduct project activities | Date: Feb 17th; Date: Mar 2nd; Week: 2 Weeks; Feb 17th-23rd Mon: Conduct project activities (2 Weeks)
Explore alternative solutions | Date: Feb 24th; Date: Mar 9th; Week: 2 Weeks; Feb24th- Mar 2nd Mon: Explore alternative solutions (2 Weeks)
Evaluate own behaviours, make reccomendations for improvement | Date: Feb 24th; Date: Mar 23rd; Week: 4 Weeks; Feb24th- Mar 2nd Mon: Evaluate own behaviours, make reccomendations for improvement (4 Weeks)
Prepare and execute primary research (questionnaire) | Date: Mar 17th; Date: Mar 30th; Week: 2 Weeks; Mar 17th- 23rd Mon: Prepare and execute primary research (2 Weeks)
Analyse and prepare discussion | Date: Mar 24th; Date: Apr 6th; Week: 2 Weeks; Mar 24th- 30th Mon: Analyse and prepare discussion (2 Weeks)
Prepare project report | Date: Mar 17th; Date: Apr 6th; Week: 3 Weeks; Mar 17th- 23rd Mon: Prepare project report (3 Weeks)
Presentation | Date: Apr 7th; Date: Apr 20th; Week: 2 Weeks; Apr 7thth- 13th Mon: Presentation (2 Weeks)
Select & prep. appropriate method for audio visual presentation | Date: Apr 7th; Date: Apr 20th; Week: 2 Weeks; Apr 7thth- 13th Mon: Select & prep. appropriate method for audio visual presentation (2 Weeks)
Challenges and value gained | Date: Apr 14th; Date: Apr 20th; Week: 1 Week; April 14- 20th Mon: Challenges & value gained (1 Week)
Success of project and justified improvements | Date: Apr 7th; Date: Apr 20th; Week: 2 Weeks; Apr 7thth- 13th Mon: Success of project and justified improvements (2 Weeks)
Self-reflection on own performance | Date: Apr 7th; Date: Apr 20th; Week: 2 Weeks; Apr 7thth- 13th Mon: Self-reflection on own performance (2 Weeks)
1st Major Milestone: Proposal Completion
2nd Major Milestone: Report Completion